## WP2
WP2 - PROJECT IMPLEMENTATION

## WP3
WP3 - PROJECT COORDINATION AND EVALUATION

## WP4
WP4 - PROJECT OUTPUT TESTING AND DISSEMINATION

## Timeline
Task Name | Bucket Name | Due Date | Description
The beginning of the project | Globally | 09/01/2024
1 - coordination workshop Portugal | Working meetings of the project - coordination and evaluation | 09/30/2024 | **Meeting the partners, presenting their organizations and opportunities, division of responsibilities in the first phase of the project, presentation of the budget, agreement on the timeline of the first phase** Venue : Portugal Estimated start date : 2024-09-30 Estimated end date : 2024-10-06
Creation of AI lessons from theory and practice | Implementation - work on project goals | 11/01/2024 | **The ultimate goal of this activity is to create material for the basics of AI - theoretical lectures and exercises.** **Estimated start date : 2024-11-01Estimated end date : 2025-06-01**
2nd workshop - Slovakia | Working meetings of the project - coordination and evaluation | 03/31/2025 | **Presenting the LMS platform; presentation of material for AI theory; introducing target groups for training on working on AI tools. Coordination of further activities, evaluation of achievements** Venue : Slovakia Estimated start date : 2025-03-31 Estimated end date : 2025-04-06
Creating lessons for teachers to use AI tools | Implementation - work on project goals | 04/01/2025 | **Material for publicly available AI tools** **Estimated start date : 2025-04-01Estimated end date : 2025-08-01**
3rd midterm workshop - Serbia | Working meetings of the project - coordination and evaluation | 06/23/2025 | **Presenting the LMS platform; presentation of materials for AI exercises, and finally shaping materials for theory and exercises in AI; presentation of material for AI tools done so far. Evaluation of the first phase of the project, agreement on the second phase** Venue: Serbia Estimated start date: 2025-06-23 Estimated end date: 2025-06-26
Creation of materials for the use of AI equipment | Implementation - work on project goals | 09/01/2025 | **AI Equipment Material** **Estimated start date : 2025-09-01Estimated end date : 2026-06-01**
4 -workshop Portugal | Working meetings of the project - coordination and evaluation | 09/22/2025 | **Presentation of AI equipment of all partners, one partner conducts a mini-training of other colleagues to work on their AI equipment. agreement on material for work on AI equipment that must be found on the LMS platform.** Presentation of final material for AI tools. Venue : Portugal Estimated start date : 2025-09-22 Estimated end date : 2025-09-28
Training in using publicly available AI tools | Dissemination of the project | 09/29/2025 | Estimated start date : **2025-09-29**Estimated end date : **2025-10-31** **In the specified period, each organization is obliged to organize two workshops - two for teaching and one for non-teaching staff , from using AI tools**
Using school AI equipment | Dissemination of the project | 02/01/2026 | **Introduction of training participants to how to use school AI equipment** **Venue : Serbia Estimated start date : 2026-02-01 Estimated end date : 2026-02-28** **"AI robot race" and presentation Project AI with Augmented Reality and Meta VR**
Seminar on AI | Dissemination of the project | 03/28/2026 | Venue : **Serbia **Estimated start date : **2026-03-28 **Estimated end date : **2026-03-29** **Acquaintance of seminar participants with material from AI - theory and exercises**
5 - workshop Slovakia | Working meetings of the project - coordination and evaluation | 04/06/2026 | **Presentation of the material done so far for work on AI equipment. Another partner trains other colleagues to work on their AI equipment. Presentation of the first results of the integration of AI into regular teaching.** Venue : Slovakia Estimated start date : 2026-04-06 Estimated end date : 2026-04-12
Using school AI equipment | Dissemination of the project | 05/01/2026 | **Introduction of training participants to how to use school AI equipment** **Venue : Portugal Estimated start date : 2026-05-01 Estimated end date : 2026-05-30**
6 - final conference | Working meetings of the project - coordination and evaluation | 08/24/2026 | **Closing of the project, presentation of all project results, LMS platform, evaluation of complete material, integration of AI work in teaching and AI training of teaching and non-teaching staff.** Venue : Serbia Estimated start date : 2026-08-24 Estimated end date : 2026- 08-26
End of project | Globally | 08/31/2026
WP2 - project implementation
WP3 - project coordination and evaluation
WP4 - project output testing and dissemination

## Contract details
Payments proposal | Initial payment | 40% | 2024-11-01
| Midterm payment | 40% | August - September 2025
| Final payment | 20% | After the delivery of the final report - October / November 2026?
Bank account details | Account name
Bank name
Address of the bank
IBAN
BIC / SWIFT
| Report on: | Report date | Reporting partner:
Reports | Creation of AI lessons - theory and practical exercises | 2025-06-01 | Serbia
| Creating lessons for teachers to use AI tools | 2025-08-01 | Slovakia
| Creation of materials for the use of AI equipment | 2026-06-01 | Portugal
| 1 - coordinating TNM meeting | 2024-12-01 | Portugal
| 2 - workshop | 2025-04-01 | Slovakia
| 3 - midterm workshop / TNM | 2025-07-01 | Serbia
| 4 - workshop | 2025-10-01 | Portugal
| 5 - workshop | 2026-04-01 | Slovakia
| 6 - final TNM meeting | 2026-08-01 | Serbia
| Training in using publicly available AI tools | 2025-11-01 | Slovakia
| Training in using publicly available AI tools | 2025-11-01 | Portugal
| "Race of AI robots" and presentation of AI project with augmented reality and Meta VR | 2026-03-01 | Serbia
| Seminar in AI technologies | 2026-02-01 | Slovakia
| Training in using publicly available AI tools | 2025-11-01 | Serbia
| Seminar in AI technologies | 2026-06-01 | Portugal